## Sheet1
POA&M ID | Affected SRs | Description | Root Cause | Recommended Remediation | Responsible Role | Priority | Estimated Effort | Target Completion | Status
poam-01 | 03.10.01, 03.10.02, 03.10.07 | Physical access controls exist but are informally managed, inconsistently documented, and lack centralized oversight. | Absence of documented physical access policies, procedures, and review mechanisms. | Develop and implement formal physical access control procedures, including visitor escort requirementes, access authorization and review processes, and documentation of access device issuance and revocation. | Facilities / Security Lead | High | Medium | 90 days | Open
poam-02 | 03.15.01 | System maintenance activities are performed but lack formal policies, approval workflows, documentation, and oversight. | Maintenance practices rely on informal processes and MSP operational knowledge rather than documented governance. | Establish and document system maintenance policies and procedures covering approval, documentation, remote maintenance authorization, tool use, and personnel responsibilities. | IT / Security Lead | High | Low | 60 days | Open
poam-03 | 03.08.01, 03.08.02, 03.08.03 | Controls governing removable media use, transport, access, and disposal are inconsistently implemented or absent. | Lack of document media protection policy enforcement mechanisms. | Develop and implement media protection procedures addressing removable media authorization, access restrictions, transport safeguards, and sanitazion prior to disposal or reuse. | IT / Security Lead | High | Medium | 90 days | Open
poam-04 | 03.03.01, 03.03.02, 03.03.03 | Audit logging exists for some systems but is inconsistently applied, reviewed, and protected. | Absence of formal audit and accountability procedures and assigned responsibilities. | Define and implement audit logging standards, log review procedures, access protections, and requirements for systems handling CUI. | IT / Security Lead | High | Medium | 90 days | Open
poam-05 | 03.01.18, 03.01.19 | Mobile devices used by field personnel are not consistenlty managed or enforced to meet CUI security requirements. | Lack of standardized mobile device management and enforcement policy. | Implement mobile device security requirements including device enrollment, encryption enforcement, access restrictions, and prohibition of unmanaged devices for CUI access. | IT / Operations | High | Medium | 90 days | Open
poam-06 | 03.14.01, 03.14.02, 03.14.03 | System flaw remediation and security alert monitoring occur informally and lack structured oversight. | Absence of documented system integrity monitoring and remediation procedures. | Establish of documented processes for vulnerability identification, remediation tracking, malware detection monitoring, and alert response for systems processing CUI. | IT / Security Lead | Medium | Medium | 120 days | Open