## Sheet1
POA&M ID | Control ID | Weakness Description | Risk Statement | Recommended Action | Responsible Role | Priority | Estimated Effort | Target Completion | Status
POA&M-AC-01 | 3.11, 3.1.2, 3.1.5 | No ducumented or consistently executed periodic user access review process exists for systems handling CUI | Unauthorized or excessive user access may persist undetected, increasing the risk of unauthorized access to CUI | Develop and implement a formal access review procedure requiring periodic (at least quarterly) review of user accounts and privileges for CUI systems, with documented approvals and remediation actions. | IT Security / Security Head | High | Low | 90 days | Open
POA&M-AC-02 | 3.1.5, 3.1.6, 3.1.7 | Local administrator privileges are granted to some users without documented justification or periodic review | Excessive privileges increase the likelihood of malware execution or unauthorized system changes impacting CUI systems. | Identify users with elevated endpoint privileges, document business justification, remove unnecessary local admin access, and implement a least-privilege enforcement policy. | IT / MSP | High | Medium | 60 days | Open
POA&M-AC-03 | 3.1.9 | System use and security warning banners are not displayed upon user login to endpoints or cloud services. | Absence of user notification weakens legal enforceability and user accountability for system misuse | Configure and deply standardize system use and security warning banners across endpoints and applicable cloud services | IT / MSP | Medium | Low | 30 days | Open
POA&M-AC-04 | 3.1.10, 3.1.11 | Session lock and timeout settings are not consistently enforced across all managed endpoints | Unattended systems may allow unauthorized access to CUI | Define standard session lock and timeout requirements and enforce them consistently using endpoint management policies | IT / MSP | Medium | Low | 45 days | Open
POA&M -AC-05 | 3.1.18, 3.1.19 | Mobile access to CUI systems is permitted without consistent enforcement of device management and encryption requirements | CUI may be accessed or stored on devices lacking adequate security controls, increasing exposure risk | Restrict mobile access to managed and encrypted devices only, or formally prohibit mobile access to CUI systems through policy and technical controls | IT / Security Lead | High | Medium | 90 days | Open
POA&M-AC-06 | 3.1.12, 3.1.15 | No formal authorization or documentation governs remote execution of privileged administrative actions | Unauthorized or undocumented adminstrative activity may occur without accountability or oversight | Define and document procedures governing remote administrative access and privileged command execution, including approval and logging requirements | IT / Security Lead | Medium | Medium | 90 days